## Overview
WORKLEDGER — Global Project Dashboard
Owner: ACI (Remy Ruozzi) ¦ Phase 1 MVP ¦ 12 Weeks ¦ Target: 10 Freelancers, 20 Jobs
Department | Owner | Progress | Tasks Done | Tasks Total | % Complete | Risk Level | Notes
CODE DEV | Claude + Remy | 52.38% | 33 | 63 | 52.38% | Medium | Sprint 1-4 done, Sprint 5 85%, Admin system built
STRATEGY | Remy + Claude | 66.67% | 10 | 15 | 66.67% | Low | Business model + MCC taxonomy finalized
DESIGN | Remy + Claude | 47.06% | 8 | 17 | 47.06% | Medium | Dark theme done, MCC design spec done, arch visualizations done
MARKETING | Remy | 0% | 0 | 10 | 0% | Low | Deferred to post-MVP polish
SECURITY | Claude + Remy | 33.33% | 5 | 15 | 33.33% | High | Key mgmt done, admin auth done, user middleware pending
LEGAL | Remy | 0% | 0 | 12 | 0% | Medium | AUSTRAC research started, structure TBD
OVERALL PROJECT |  |  | 56 | 132 | 42.42%
Sprint Timeline
Sprint | Weeks | Focus | Status | Progress | Key Deliverable | Blockers | Notes
Sprint 1 | 1-2 | Foundation | DONE | 100% | Dev env + XRPL testnet + DB | - | All complete
Sprint 2 | 3-4 | Auth & Wallet | IN PROGRESS | 80% | Registration, wallet, Xaman | Redirect bug | Xaman auth parked, Google OAuth done
Sprint 3 | 5-6 | Contracts & Escrow | IN PROGRESS | 90% | Fixed-price + escrow flow | - | Contracts + escrow + negotiation done, detail page WIP
Sprint 4 | 7-8 | NFTs & Proof | IN PROGRESS | 45% | PoW NFT minting + portfolio | IPFS setup | MCC taxonomy + design spec done, IPFS + auto-mint WIP
Sprint 5 | 9-10 | Dashboard & Polish | IN PROGRESS | 80% | Full dashboard + notifications | - | Dashboard done, admin system done, n8n done, notifications WIP
Sprint 6 | 11-12 | Testing & Launch | NOT STARTED | 0% | E2E testing + mainnet deploy | - | Depends on all above

## Code Dev
# | Task | Description | Sprint | Status | Priority | Assignee | Files / Notes | 33 | 63
[8 empty] | 34 | 63
Sprint 1
1 | Project scaffolding | Next.js 14 + TS + Tailwind setup | Sprint 1 | DONE | Critical | Claude | Complete
2 | XRPL client manager | Singleton connection with auto-reconnect | Sprint 1 | DONE | Critical | Claude | src/lib/xrpl/client.ts
3 | Wallet generation | Keypair generation + trust lines | Sprint 1 | DONE | Critical | Claude | src/lib/xrpl/wallet.ts
4 | Escrow system | Create/finish/cancel with crypto-conditions | Sprint 1 | DONE | Critical | Claude | src/lib/xrpl/escrow.ts
5 | NFT minting engine | PoW, License, Access Pass minting | Sprint 1 | DONE | High | Claude | src/lib/xrpl/nft.ts
6 | Database schema | 7 tables + RLS + indexes + triggers | Sprint 1 | DONE | Critical | Claude | supabase/migrations/001
7 | Supabase clients | Browser + server client setup | Sprint 1 | DONE | Critical | Claude | src/lib/supabase/
8 | Type definitions | All entity types | Sprint 1 | DONE | High | Claude | src/types/index.ts
9 | Zustand wallet store | State mgmt with Xaman provider | Sprint 1 | DONE | High | Claude | src/stores/wallet-store.ts
Sprint 2
10 | Landing page | Hero, value props, CTA | Sprint 2 | DONE | High | Claude | src/app/page.tsx
11 | Login page | Xaman + Google OAuth buttons | Sprint 2 | DONE | Critical | Claude | src/app/(auth)/login/page.tsx
12 | Google OAuth | Supabase Auth with Google provider | Sprint 2 | DONE | Critical | Claude+Remy | Vercel env configured
13 | Xaman SDK wrapper | QR modal, deep link, WebSocket | Sprint 2 | DONE | Critical | Claude | src/lib/xaman/
14 | Xaman auth flow | SignIn verify + Supabase session | Sprint 2 | DONE | Critical | Claude | src/app/api/auth/xaman/
15 | Admin Supabase client | Service role for user creation | Sprint 2 | DONE | Critical | Claude | src/lib/supabase/admin.ts
16 | Xaman redirect fix | useEffect-based redirect after sign | Sprint 2 | PARKED | Medium | Claude | Bug: redirect not firing consistently
17 | Auth middleware | Route protection for dashboard | Sprint 2 | IN PROGRESS | High | Claude | Admin middleware done (withAdmin), user middleware pending
18 | Wallet display page | Balance card + currency toggle | Sprint 2 | NOT STARTED | High | Claude | src/app/(dashboard)/wallet/
19 | Transaction history | Recent XRPL tx list | Sprint 2 | NOT STARTED | Medium | Claude | TransactionList component
Sprint 3
20 | Contract creation form | Fixed-price template form | Sprint 3 | DONE | Critical | Claude | FixedPriceForm component
21 | Contract generation engine | Form input to XRPL params | Sprint 3 | DONE | Critical | Claude | src/lib/contracts/generator.ts
22 | Contract API routes | CRUD endpoints | Sprint 3 | DONE | High | Claude | src/app/api/contracts/
23 | Milestone escrow API | Fund/release with Xaman support | Sprint 3 | DONE | Critical | Claude | milestones/[seq]/route.ts
24 | Retainer contract | Recurring escrow template | Sprint 3 | DONE | High | Claude | retainer-escrow.ts
25 | Escrow WebSocket listener | Real-time funding confirmation | Sprint 3 | NOT STARTED | High | Claude | src/lib/xrpl/listener.ts
26 | Contract detail page | Status, milestones, parties view | Sprint 3 | IN PROGRESS | High | Claude | Contract detail view built in session 15-16
27 | Platform fee deduction | 2% on escrow release | Sprint 3 | IN PROGRESS | Medium | Claude | 0.98% fee in release flow, fee_ledger table ready
Sprint 4
28 | IPFS/Pinata upload | NFT metadata JSON to IPFS | Sprint 4 | NOT STARTED | High | Claude | src/lib/ipfs/pinata.ts
29 | Auto-mint on approval | PoW NFT in escrow release flow | Sprint 4 | IN PROGRESS | High | Claude | Mock mint in test mode, MCC-DESIGN.md spec complete
30 | Deliverable hashing | SHA-256 of uploaded files | Sprint 4 | NOT STARTED | Medium | Claude | src/lib/utils/hash.ts
31 | NFT portfolio page | Grid view of all NFTs | Sprint 4 | IN PROGRESS | High | Claude | MCCPortfolio + MCCCard spec in MCC-DESIGN.md
32 | NFT taxonomy rename | PoW->Work Credential, AP->Membership | Sprint 4 | DONE | Medium | Remy+Claude | MCC: Work Credential (T1), License (T2), Access Pass (T3), Client Completion (T4)
33 | Public profile page | User profile + NFT portfolio | Sprint 4 | NOT STARTED | Medium | Claude | profile/page.tsx
34 | Reputation scoring | On-chain avg rating + job count | Sprint 4 | NOT STARTED | Medium | Claude | src/lib/reputation.ts
35 | Client rating flow | 1-5 stars + comment after approval | Sprint 4 | NOT STARTED | Medium | Claude | RatingForm component
Sprint 5
36 | Dashboard home page | Overview stats, active contracts | Sprint 5 | DONE | High | Claude | dashboard/page.tsx
37 | Sidebar navigation | Links to all sections | Sprint 5 | DONE | High | Claude | Sidebar.tsx
38 | Dashboard wireframes | Bento grid layout concept | Sprint 5 | DONE | Medium | Claude | docs/dashboard-wireframes.jsx
39 | Earnings chart | Visual earnings over time | Sprint 5 | NOT STARTED | Medium | Claude | EarningsChart component
40 | Responsive design | Tablet + mobile layouts | Sprint 5 | NOT STARTED | Medium | Claude | Tailwind responsive
41 | Email notifications | Escrow events email alerts | Sprint 5 | NOT STARTED | Medium | Claude | src/lib/notifications.ts
42 | In-app notifications | Bell icon + dropdown | Sprint 5 | NOT STARTED | Medium | Claude | NotificationBell component
43 | Settings page | Profile, avatar, skills, payout | Sprint 5 | NOT STARTED | Medium | Claude | settings/page.tsx
44 | Error handling | Graceful error states | Sprint 5 | NOT STARTED | Medium | Claude | All components
45 | Loading states | Skeleton screens | Sprint 5 | NOT STARTED | Low | Claude | All pages
Sprint 6
46 | End-to-end testing | Full job lifecycle with 2 accounts | Sprint 6 | NOT STARTED | Critical | Claude+Remy | Create->Fund->Deliver->Approve->NFT
47 | Edge case testing | Escrow expiry, cancellation | Sprint 6 | NOT STARTED | High | Claude | All status transitions
48 | Security review | Key storage, auth, API auth | Sprint 6 | NOT STARTED | Critical | Claude+Remy | All API routes
49 | Cross-browser testing | Chrome, Firefox, Safari, mobile | Sprint 6 | NOT STARTED | Medium | Remy | Manual testing
50 | Deploy to Vercel | Frontend production deployment | Sprint 6 | IN PROGRESS | Critical | Remy | Already deploying iteratively
51 | Mainnet switch | XRPL testnet -> mainnet | Sprint 6 | NOT STARTED | Critical | Claude+Remy | Update .env
52 | Domain setup | workledger.io DNS config | Sprint 6 | NOT STARTED | High | Remy | DNS settings
53 | Invite first 10 freelancers | Personal outreach | Sprint 6 | NOT STARTED | High | Remy | Email + social
Session 17-18
54 | MCC visual design spec | Full credential card design: 4 taxons, guilloche, animations, typography | Sprint 4 | DONE | High | Claude | docs/MCC-DESIGN.md — federal certificate aesthetic
55 | Architecture visualizations | 15 files: React interactive, Three.js 3D, Mermaid, HTML, SVG diagrams | Sprint 5 | DONE | Medium | Claude | docs/Architecture/ — all formats
56 | n8n event system client | 14 webhook events, fire-and-forget, 5s timeout | Sprint 5 | DONE | High | Claude | src/lib/n8n/client.ts + hermes skills
57 | Admin auth library | bcrypt passwords, SHA-256 sessions, permission checks, audit log | Sprint 5 | DONE | Critical | Claude | docs/Admin-API/lib/admin-auth.ts
58 | Admin API routes | /api/admin/login, logout, me, disputes, stats — withAdmin middleware | Sprint 5 | DONE | Critical | Claude | docs/Admin-API/api/admin/ (5 routes)
59 | Admin dashboard UI | Login page + 3-tab dashboard (overview, disputes, accounts) | Sprint 5 | DONE | High | Claude | docs/Admin-API/app/admin/ (login + main)
60 | Boss account seed script | Seeds remy@studioledger.ai as boss role, bcrypt, audit logged | Sprint 5 | DONE | Critical | Claude | docs/Admin-API/scripts/seed-boss.ts
61 | Admin DB migration (015) | 6 tables: admin_accounts, sessions, audit_log, permissions, arbitrators, panels | Sprint 5 | DONE | Critical | Claude | supabase/migrations/015_admin_accounts.sql
62 | Hermes AI skills (7) | Debug skills: xrpl-diag, escrow-debug, mcc-mint-verify, n8n-wire, etc. | Sprint 5 | DONE | Medium | Claude | docs/hermes-skills/ (7 .md files)
63 | Contract negotiation system | Proposals, counter-proposals, amendment tracking, DB migration 014 | Sprint 3 | DONE | High | Claude | supabase/migrations/014 + API routes

## Strategy
# | Task | Description | Category | Status | Priority | Notes | 10 | 15
[7 empty] | 10 | 15
1 | Business model definition | Fee structure: 0.98% platform fee on escrow release | Revenue | DONE | Critical | Updated to 0.98% in session 13+
2 | Target user personas | Phase 1: Web3 freelancers, Phase 2: international $30-100K | Market | DONE | High | 3-phase growth plan documented
3 | Competitive positioning | Web2 comparison (Upwork, Fiverr, Deel, PayPal) | Market | DONE | High | PDF report generated
4 | Growth strategy doc | Market entry, pain points, advantages | Market | DONE | High | PDF report generated
5 | NFT taxonomy design | Work Credential / License / Membership naming | Product | DONE | High | MCC: 4 taxons defined in MCC-DESIGN.md
6 | Smart contract taxonomy | 10 contract types mapped to WorkLedger | Product | DONE | Medium | Fixed-price + milestone impl
7 | Currency strategy | RLUSD primary + GateHub fiat + XRP native | Product | DONE | High | 8 currencies configured
8 | i18n priority list | JP > ES > PT > FR > AR > ZH > RU | Growth | DONE | Medium | Japanese first market
9 | Team scaling triggers | 50u->CM, 100->Dispute, 200->Dev, 500->Legal | Ops | DONE | Medium | Documented in CLAUDE.md
10 | UX philosophy | Product power + ergonomics first, marketing later | Product | DONE | High | Remy's direction
11 | Wallet as gateway | Wallet is primary user entry point | UX | PLANNED | High | Design around wallet-first UX
12 | Client vs freelancer modes | Distinct color schemes per role | UX | PLANNED | Medium | Phase 2 feature
13 | Negotiation workspace | Structured client-freelancer negotiation | Product | PLANNED | Medium | Phase 2 feature
14 | Photographer/filmmaker use cases | Tailored contract templates for creatives | Market | PLANNED | High | Remy's domain expertise
15 | Department AI workflow | 6 depts with parallel AI agents | Ops | PLANNED | Medium | Needs Claude Max

## Design
# | Task | Description | Category | Status | Priority | Notes | 8 | 17
[7 empty] | 7 | 17
1 | Dark Web3 theme | Dark background, brand purple, glow accents | Theme | DONE | Critical | globals.css + Tailwind config
2 | Color system | Brand purple #6C63FF + semantic colors | Theme | DONE | High | CSS custom properties
3 | Dashboard wireframes | Bento grid + command center concepts | Layout | DONE | High | docs/dashboard-wireframes.jsx
4 | Login page design | Xaman + Google CTA, dark card style | Pages | DONE | High | Deployed and working
5 | Landing page design | Hero, value props, CTA sections | Pages | DONE | High | Deployed
6 | Component library | Buttons, cards, forms, modals, badges | Components | IN PROGRESS | High | XamanSignModal done, more needed
7 | Wallet UI design | Balance cards, currency toggle, tx list | Pages | NOT STARTED | High | Wallet-first UX approach
8 | Contract UI design | Creation form, detail view, status flow | Pages | NOT STARTED | High | Template-based approach
9 | NFT portfolio design | Grid view, detail cards, metadata display | Pages | IN PROGRESS | Medium | MCC-DESIGN.md: full card anatomy, animations, typography, print/export
10 | Sidebar/navigation design | Responsive sidebar with role context | Layout | IN PROGRESS | High | Basic done, needs polish
11 | Mobile responsive design | Tablet + phone breakpoints | Layout | NOT STARTED | Medium | Tailwind responsive classes
12 | Icon system | Lucide React icons throughout | Components | IN PROGRESS | Low | Already using lucide-react
13 | Loading/skeleton states | Consistent loading UX | Components | NOT STARTED | Medium | All pages need these
14 | Error state designs | Graceful error display patterns | Components | NOT STARTED | Medium | Consistent across app
15 | Onboarding flow design | First-time user walkthrough | UX | NOT STARTED | Medium | Tooltips + guided setup
16 | Architecture visualizations | 15 files: interactive React, 3D Three.js, Mermaid, HTML, SVG | Docs | DONE | Medium | docs/Architecture/ — all formats for browser viewing
17 | MCC credential card design | Federal certificate aesthetic: guilloche, seals, 4 taxon palettes | Components | DONE | High | MCC-DESIGN.md: MCCCard, MCCPortfolio, MCCPrintView specs

## Marketing
# | Task | Description | Phase | Status | Priority | Notes | Done | Total
[7 empty] | 0 | 10
1 | Brand identity | Logo, color palette, typography guide | Pre-launch | NOT STARTED | High | Dark Web3 aesthetic defined
2 | Landing page copy | Hero text, value props, CTAs | Pre-launch | PLANNED | Medium | After product UX finalized
3 | XRPL community outreach | Engage XRPL devs and community | Phase 1 | PLANNED | High | First 10 users from here
4 | Social media presence | Twitter/X, LinkedIn profiles | Phase 1 | NOT STARTED | Medium | Consistent branding
5 | Demo video | 2-min product walkthrough | Phase 1 | NOT STARTED | Medium | After MVP stable
6 | Freelancer testimonials | Case studies from first users | Phase 1 | NOT STARTED | Low | After 10 users onboarded
7 | Content strategy | Blog posts on XRPL + freelancing | Phase 2 | NOT STARTED | Low | SEO + thought leadership
8 | International launch (JP) | Japanese localization + outreach | Phase 2 | NOT STARTED | Medium | First i18n market
9 | Partnership outreach | Creative agencies, photo studios | Phase 2 | NOT STARTED | Medium | Remy's network
10 | Referral program design | Incentive structure for growth | Phase 2 | NOT STARTED | Low | After product-market fit

## Security
# | Task | Description | Category | Status | Priority | Notes | 5 | 15
[7 empty] | 5 | 15
1 | Encrypted seed storage | crypto.createCipheriv for wallet seeds | Key Mgmt | DONE | Critical | In auth register flow
2 | Service role isolation | Admin client separated from browser client | Auth | DONE | Critical | src/lib/supabase/admin.ts
3 | RLS policies | Row-level security on all tables | Database | DONE | Critical | In migration SQL
4 | Env var management | Secrets in .env.local, not in code | Config | DONE | Critical | Vercel env vars configured
5 | Multi-sign wallet (2-of-3) | User + platform + recovery key | Key Mgmt | NOT STARTED | Critical | Sprint 2+ planned
6 | API route authorization | Verify auth on all protected endpoints | Auth | IN PROGRESS | Critical | Admin withAdmin() middleware done, user routes pending
7 | Input validation (Zod) | Validate all API inputs with Zod | API | NOT STARTED | High | At API boundaries
8 | Rate limiting | Prevent API abuse | API | NOT STARTED | High | Vercel Edge or custom
9 | XRPL tx verification | Verify on-chain before DB update | Blockchain | NOT STARTED | Critical | Trust but verify pattern
10 | Escrow condition security | Crypto-conditions properly generated | Blockchain | DONE | Critical | five-bells-condition lib
11 | XSS prevention | Sanitize all user inputs in UI | Frontend | NOT STARTED | High | React auto-escaping helps
12 | CSRF protection | Token-based request validation | API | NOT STARTED | Medium | Next.js built-in + custom
13 | Security audit checklist | Pre-launch security review | Audit | NOT STARTED | Critical | Sprint 6 task
14 | Data backup strategy | Supabase backup + XRPL immutability | Ops | NOT STARTED | High | Supabase auto-backup on paid
15 | Incident response plan | What to do if breach detected | Ops | NOT STARTED | Medium | Document before mainnet

## Legal
# | Task | Description | Category | Status | Priority | Notes | 0 | 12
[7 empty] | 0 | 12
1 | Company structure decision | Sole trader vs Pty Ltd vs offshore | Entity | NOT STARTED | High | Australia or Singapore?
2 | Terms of Service | Platform usage terms | Docs | NOT STARTED | Critical | Before mainnet launch
3 | Privacy Policy | GDPR + Australian Privacy Act compliant | Docs | NOT STARTED | Critical | Before mainnet launch
4 | KYC requirements analysis | When/if KYC needed for XRPL escrow | Compliance | NOT STARTED | High | Deferred for beta
5 | AML/CTF assessment | Anti-money laundering obligations | Compliance | IN PROGRESS | High | AUSTRAC enrollment research done (docs/AUSTRAC.md, AUSTRAC-ENROLLMENT.md)
6 | RLUSD regulatory status | NYDFS regulated stablecoin implications | Compliance | PLANNED | Medium | Research needed
7 | OFAC sanctions compliance | Blocked countries/addresses list | Compliance | NOT STARTED | High | Critical for mainnet
8 | Escrow legal framework | Smart contract as legal agreement? | Legal | NOT STARTED | Medium | Depends on jurisdiction
9 | NFT IP rights | Work Credential ownership + licensing | IP | NOT STARTED | Medium | Part of taxonomy design
10 | Dispute resolution policy | Arbitration flow + fee structure | Policy | PLANNED | Medium | 5% from losing party
11 | Tax reporting obligations | GST/VAT on platform fees | Tax | NOT STARTED | Medium | Accounting setup needed
12 | Open source licensing | MIT or proprietary for codebase | IP | NOT STARTED | Low | Decide before public repo